STUDENT SAMPLE II

Professor Kate Boisvert, Astronomy 10

# Honors Contract Proposal

1.  Project Goal, Objectives and Thesis:  The goal of my project is to learn how to navigate a sailboat on the ocean, out-of-sight of land, using only the principles of celestial navigation.

2.  Project Outcomes:  The outcome for this project will be a successful journey from the San Francisco to Monterey using the celestial navigation skills I have acquired.  Evidence of this journey will include a 10-page minimum journal of the learning process and actual journey, photos, and a video which will be used in a presentation before my entire astronomy class.

3.  Project Resource List

Books:  The Nautical Almanac

Celestial Navigation for Yachtsmen, Mary Blewitz

The Boater’s Bowditch,

Navigation and Plotting, Dutton

Other Sources:  Celestial Navigation seminars offered through Cal Adventures

4. Project Process & Timeline

Weeks			Process			Meeting Schedule  & Outcomes

1-3		Develop project outline		At least 2 meetings with Prof.

Find potential sources			Boisvert

Write Honors Proposal

PROPOSAL TURNED IN TO

HONORS BOARD BY SEPTEMBER 10th

4-7		Begin research				Meetings every other Thursday

Take 2-day seminar			with Prof. Boisvert

PRACTICE 1-HOUR JOURNEY BY OCT 6

8-11		Take advanced seminar		Meetings every other Thursday

PRACTICE 2-HOUR JOURNEY BY NOV 3

12-14		Plot out SF-Monterey			Meetings every other Thursday

trip		FINAL PLANS TO PROF.

BOISVERT BY NOV. 24

15		Do the journey	!			TRIP DONE BY DECEMBER 1

16		Prepare Presentation			Meet with Prof. Boisvert as a

“test run”

17		Give Presentation			PRESENTATION & JOURNAL

to class					COMPLETED BY DEC. 6

Turn in Journal