ACCREDITATION RESPONSE TASK FORCE

Minutes of May 5, 2009 Meeting

Present:  Peter Garcia, Christina Goff, Ruth Goodin, Adam Jacobs, Kiran Kamath, Denise Knowles, Richard Livingston, Gail Newman, Michael Norris, Pam Perfumo, Gil Rodriguez, Tue Rust, Janice Townsend, Julie Von Bergen, Debbie Wilson, and Nancy Ybarra.

Excused: Len Price, Joellen Hiltbrand,

| TASK #1: Develop a plan to determine how all the course outlines will be updated with SLOs and submitted to the Office of Instruction by January 29, 2010 for Curriculum Committee review and approval. |
| --- |
| Activity | Who will be responsible | Completed by (date) |
| Update on course outline grids from the department chairs: Almost all the grids have been received on time Deans will follow up with the chairs who have not yet responded Reminder process needs to be developed to ensure course outlines are updated per grid | Kiran, Gil Kiran will work IT and Eileen | May 15, 2009 June 8, 2009 |
| Update on “Camp Course Outline” Camps are being held on the remaining Fridays during the spring semester During the summer, camps will be held on Tuesdays. 24 faculty have responded expressing interest. Camps will be offered during flex in August 2009 More coaches need to be recruited and trained | Janice | On going |
| COOR gauge online: Gauge will be updated as soon as the COOR is recommended for approval by the Curriculum Committee and any changes are completed. Course outlines not approved by the President/designee will result in COOR gauge update being reversed. | Kiran will inform Eileen about update schedule. | May 6, 2009 |

| TASK #2: Develop a plan to determine how the assessment cycle (planning, assessing, report, and implementing results) will be completed at the course level by every instructional program by March 31, 2011. |
| --- |
| Activity | Who will be responsible | Completed by (date) |
| The home grown automation tool was discussed and a basic demonstration of the product was viewed. More detailed demonstration of the capability of the home grown automation tool in the Sharepoint program | Denise | May 20, 2009 |
| Comments to include when designing the product were: Individual CSLO level data must be compiled at the PSLO level and again at the highest level (ISLO) Include bar charts on each CSLO, PSLO and ISLO to assess level at a glance at the course, program and institutional levels. Quantitative and qualitative data should be considered. Ed plans must be included as a variable for Development English and Developmental Math Information must be imported from Datatel and Curricunet Information must be ‘locked’ when data entry is completed by course instructor at the end of the course. Remove variable called “participation Modify evaluation for “attendance” – use ‘high, medium and low” – so there is no misunderstanding that attendance is being ‘graded’. Include a content sheet. THIS NEEDS TO BE DEFINED CLEARLY. “Grey out” students who have dropped the course. They should not be eliminated from the list of students in the course. Determine when faculty can begin inputting data. |  |  |
| Straw vote was taken on which assessment software program LMC should adopt and recommend to the President: Curricunet – Purchase an assessment module? Ellumin? Home grown product in Sharepoint? The Task Force voted unanimously to recommend adopting the home grown product after the discussions and demonstrations over the last 3 meetings. Rationale: Easy to use and train faculty on Can be modified as needed quickly Low cost to develop The product will continue to be developed. | Kiran | May 13, 2009 |
| Professional Development: To succeed, faculty will need to be trained and supported to conduct Course Level Assessment and to use the automation tool (technical training). Professional Development will need to be offered during all the phases – planning, gathering results, documenting results, implementing changes for improvement | Ruth |  |
| Next Steps: Campus Communication draft re Task Force work The automation product will continue to be developed. An automation subgroup will meet to define the variables in more detail. Volunteers are Denise, Adam, Kiran, Michael, Julie, Debbie, Tue, Ken, and Janice. A professional development subgroup will meet to have an in depth discussion. Volunteers include Nancy, Ruth, Richard, Gil, Janice, and Christina. The entire task force will meet for a more in detailed demonstration of the automation tool and to discuss the professional development plan. | Michael Denise Automation subgroup Professional development subgroup Full Task Force | May 12, 2009 May 20, 2009 May 12, 2009 (3-5 pm) May 12, 2009 (2-4 pm) May 20, 2009 (1-3 pm) |
| Agenda for meeting on May 20: Demonstration of automation tool Discuss professional development plan Plan to be submitted to the Accreditation Commission Any pending items | Denise Nancy and Ruth All | May20, 2009 |

| TASK #3: Have a plan in place by May 22, 2009 about tasks #1 and #2 to include in the report to the commission. Report to the Commission is due by October 15, 2009. |
| --- |
| Activity | Who will be responsible | Completed by (date) |
| Develop the plan for Task #1 | Accreditation Response Task Force | April 3, 2009 |
| Develop the plan for Task #2 | Task Force and TLP | May 22, 2009 |
| Submit plan to Richard Livingston to be included in the Follow-up Report. | Kiran and Accreditation Task Force | May 22, 2009 |

Unfinished business to keep track of:

| Activity | Who will be responsible | Completed by (date) |
| --- | --- | --- |
| Recruit curriculum and assessment coaches | Janice, ?? | On going |
| Email reminders to faculty for course outlines updating | Kiran with IT and Eileen | On going |
| Consider delaying the launch of “Curricunet” from Fall 2009 to Spring 2010. Do soft launch in Fall 2009 with some faculty. | Janice and Gil |  |
| “Strengthening Student Success” conference in October 9-11, 2009. Recruit faculty to attend. Funding required. | Richard |  |
| Select courses to be assessed each semester starting with Spring 2010 in collaboration with Department Chairs. | Gil and Kiran | August 31, 2009?? (to be finalized) |