- Did you complete the activities listed in the proposal? If not, what changes were made?

| 1 Assessment | Yes, pilots are on track |
| --- | --- |
| 2 Counseling | All goals partially completed, Products in draft form |
| 3 Engineering | Exceeded goal, wrote 7 rather than 5 outlines. Waiting on program approval. |
| 4 English DE | Yes, completed all activities listed. Details available on Blackboard. |
| 5 Math DE | Three math teaching communities completed all activities in the proposal |
| 6 Travel | Yes, developed and offered 3 online courses |

- Your project was allocated the following amount: _________

How much of the allocation did you spend?

| 1 Assessment | $23100; spent $14,427.69: Load was used instead. |
| --- | --- |
| 2 Counseling | $13,200; spent $2200 on training, $11- materials & supplies, 50 hours non-instructional |
| 3 Engineering | $9296; spent $8887.78: don’t anticipate any more spending. |
| 44 4 English DE | $12,300; spent $6632.38: smaller participation than budgeted for. |
| 5 Math DE | $12.300; spent $11,442.51 |
| 6 Travel | $3263; spent $3263 |

- Did you achieve the expected outcomes of the proposal? If not, what outcomes were achieved?

| 1 Assessment | Yes, achieved the outcomes specified. |
| --- | --- |
| 2 Counseling | Goals and objectives are in progress |
| 3 Engineering | Yes, so far. Waiting for state approval |
| 4 English DE | Yes, achieved the outcomes of the proposal |
| 5 Math DE | Each teaching community produced the expected outcomes |
| 6 Travel | Yes, offered fully online courses, high completion rates, increased certificates |

- Did the project support the unit goal(s)? How?

| 1 Assessment | N/A |
| --- | --- |
| 2 Counseling | Yes, improved online information relating to counseling |
| 3 Engineering | Yes, unit goals included a new engineering program |
| 4 English DE | Yes, units goals call for assessment |
| 5 Math DE | Yes, develop DE math program and improve quality of instruction |
| 6 Travel | Yes, partnered with organizations, increased enrollments and met VATEA criteria |

- Did the project address the strategic goal identified in the proposal? Describe the effect the proposal had on the strategic goal.

| 1 Assessment | Project directly addressed number 1 goal |
| --- | --- |
| 2 Counseling | Yes, the goal of expanding use of technology and goal of providing more services |
| 3 Engineering | Yes, better satisfies needs of engineering students and writing ed plans |
| 4 English DE | Yes, goal #1: assessment and goal #2: increase # students achieving ed goal |
| 5 Math DE | Yes, goal #1: assessment and goal #2: increase # students achieving ed goal |
| 6 Travel | Yes, listed above in #3 and #4 |