# ANNUAL OFFICE OF INSTRUCTION PROGRAM REVIEW AND PLANNING PROGRESS

# FALL 2008

- What is the status of the objectives identified in your Fall 2006 Action Plan: Program Priorities and/or your Fall 2007 Annual Progress Plan? Please be as complete as possible. Add rows as necessary:

| OBJECTIVE | COMPLETED, REVISED, IN PROGRESS, ETC. | COMMENTS |
| --- | --- | --- |
| 1 Improve processes and services | Pretty good progress. Ongoing objective. | Load sheet process is improved. Grid collection better. Course outline process better but needs constant attention. Special admit orientation completely online. |
| 2 Improve communication | Good progress. Also ongoing. | Office website up and running and being used. Department chair meetings are more effective, good attendance this Fall. Email distribution lists seem to work. |
| 3 Be more proactive in the development of new curriculum, programs and services | In progress. | Occ Ed has done well with new programs/curriculum. ESL is being revised. Environmental Sciences has started but needs enrollments. Puente is going well again. Umoja has started and seems strong. Need more degree programs in LAS. |
| 4 Professional development. | Ongoing and restarting. | Task force is working on the development of a program. Some activities have been facilitated by the office. This is an emphasis in the program review/plan update this Fall. |
| 5. Improve Office of Instruction communication and workflow | Ongoing, working on this. | The deans meet twice a month and communication is good. We have started meeting with office staff once a month. We should assess the results. |

- What are new objectives that you have identified as a result of changes in the environment, data or other since Fall 2007?

| OBJECTIVE | ACTIVITIES | DESIRED OUTCOMES | LEAD | TIMELINE |
| --- | --- | --- | --- | --- |
| 1 Coordinate and support the update of COORs | Work with the curriculum committee and departments. Seek compensation and resources | All COORs updated per Title 5 regulations | Deans | From now to Nov. 2010 |
| 2 Complete office move to 4th level of core building | Plan move and implement | Moved in and ready to go for Summer 2009 | Richard Livingston | Complete move by June 2009 |
| 3 Complete the Block Schedule study | Participate in the task force. Monitor process. | Good decision on scheduling | Richard Livingston | May 2009 |
| 4 Improve faculty/staff record submissions | Work with A & R. Effectively communicate with faculty/staff | All students enrolled by 1st census. All rosters and hours submitted on time. | Deans | Ongoing |
| 5. Improve program assessment of SLOs | Support TLP and programs in assessment activities | Each program should complete one assessment cycle by the end of the year | Deans, SAM | June 2009 |

FALL 2008 progress update: Office of Instruction