ACCREDITATION RESPONSE TASK FORCE

Minutes of April 21, 2009 Meeting

Members present:  Christina Goff, Adam Jacobs, Kiran Kamath (facilitator), Denise Knowles, Richard Livingston, Cherry Li- Bugg, Cindy McGrath, Gail Newman, Gil Rodriguez, Leonard Price Tue Rust, Janice Townsend, and Nancy Ybarra, Debbie Wilson.

Members excused – Ken Alexander, Joellen Hiltbrand, Michael Norris, Pam Perfumo

| TASK #1: Develop a plan to determine how all the course outlines will be updated with SLOs and submitted to the Office of Instruction by January 29, 2010 for Curriculum Committee review and approval. |  |  |
| --- | --- | --- |
| Activity | Who will be responsible | Date of Completion |
| - Update: - Information was provided to Dept Chairs on 4/7/09 - Dept chairs will complete a form indicating who will update each course outline and by when. It will be returned to the deans. Deans will send out reminders if necessary. - A course outline update gauge will be posted online - Email blast will go out regularly campus-wide with a progress update. | Richard Livingston Kiran and Gil Kiran, Eileen, Eloine Kiran | April 7, 2009 April 30, 2009 April 27, 2009 Ongoing till January, 2010. |

| TASK #2: Develop a plan to determine how the assessment cycle (plan, assessment, report, and implement results to improve teaching and learning) will be completed at the course level by every instructional program by spring 2011. |  |  |
| --- | --- | --- |
| Activity | Who will be responsible | Completed by (date) |
| - Selection of courses to be assessed: - Gil and Kiran shared a draft of courses that could be assessed in Spring 2010, Fall 2010 and Spring 2011. - More courses will need to be assessed in Fall 2010 and Spring 2010 to reach our targets of 15% each semester. - Deans will work with department chairs/program leads to develop a final list and share the list with the task force | Kiran and Gil Kiran and Gil | Mid May, 2009 |
| - Automation for CSLO Assessment: Denise, Adam and Cherry had studied the pros and cons of Curricunet, Elumin and the DVC homegrown product. They discussed an LMC home grown product which could gather quantitative and some qualitative data of Course level SLOs. Regardless of which product LMC adopts, the basic principles of good practice we discussed were: - The results should be meaningful, and not just busy-work to be in compliance. - It should be easy for everyone to use and should need very little training. - We should consider the total cost of the automation tool which includes time to learn to use it, input data and gather results. - The program should be able to compile SLOs data from the course level to the program level to the institutional level with the click of a button! There was discussion about the source of the data, what data and other variables/information to gather etc. The committee is leaning towards customizing a homegrown product, but has not yet eliminated the other options (Curricunet and Elumin) | Task Force and TLP | Mid May, 2009 |
| - Next Steps: - Automation sub group will meet on April 29 from 3 pm to 4:30 pm. Room 409. - Entire Task force will meet on May 5 from 2 pm to 4 pm in Library conference room #12. - Agenda for the meeting on May 5: - Automation - Professional Development - Select dates and finalize timeline to include in report to Accreditation Commission report due in October, 2009. |  |  |