## New_EMP_Sharing
LMC Mission/Vision/Value and Educational Master Plan 2020-2025 Planning Process, Task, and Timeline (DRAFT 9.24.2019)
Key Planning Process | Task
Kick Off Educational Master Plan 2020-2025
Sept 11, 2019 | 1. Meet with EMP liaison and President's Cabinet to review the proposed Mission/Vision/Value and EMP workplan; activities, timelines, responsibilities, and draft of communications plan.
Sep 12-Sept 24 | 2. Meet with College leaders (Senates' presidents) to review the proposed Mission/Vision/Value and EMP workplan; activities, timelines, responsibilities, and draft of communications plan.
Sept 30, 2019 | 3. College Assembly: Mission/Vision/Value workshops and forum + EMP Overview Mission/Vision/Value (with focus on identification of stakeholders, formal and informal mandates/purposes, & "Six Key Organizational Questions") + overview of EMP purpose and development process
Oct 3 (Planning Committee) | 4. Meet with the EMP Core Committee to discuss overall planning activities, timeline, responsibilities, and communication plan actions and methods. Gather input on the current planning process and structure and approach to integration.
Environmental Scan
Oct--Dec. 2019 | 5. Conduct an assessment of existing plans to identify linkages (e.g., use RP Group’s Crosswalk of College Plans and Processes and Accreditation Standards) between and among plans, identify planning gaps, and develop an approach to address gaps.
6. Determine data sets for environmental scan, prepare additional data, and conduct environmental scan analysis. Draft planning assumptions and implications.
7. Administer SOAR survey (Nov 8-20) to all constituent groups (e.g., advisory groups, external partners, etc.), and analyze results.
8. Collect and synthesize instructional program and support services information, strengths, challenges, and opportunities, (including program reviews and interviews with program/unit/area representatives).
Nov 7 (Planning Committee) | 9. Planning Committee: review #5 (results), #6 (results), #7 (review SOAR survey questions)
Dec 5 (Planning Committee) | 10.Planning Committee: review #7 (results) and #8 (results)
College Forums: Identify Collegewide key issues, strategies and opportuities
January 24, 2020 (College Opening Day) | 11. College Opening Day: Mission/Vision/Value + EMP progress (#5,6,7,8,9,10)
February (3 College Forums) | 12. Meet with faculty, classified professionals, deans, other administrators and students to gain input on program and services strengths and opportunities (e.g., college forums). Three EMP Forums in February. We could incorporate the information/analysis gathered in #5,6,7,8,9,10,11.
March 6 (Planning Committee whole day) | 13. Facilitate a one-day planning retreat to review college forums input, scan data, SOAR results, program and services information to include the following: (#5,6,7,8,9,10,11,12) 1. Identify emerging themes 2. Connect with SEM 3. Draft goals (a) and objectives (b) and key action steps (c)
Goal Setting
March-April | 14. Develop key performance indicators (KPI) (d) and metrics (e)for the EMP goals.
Draft EMP
April 9, 2020 (Planning Committee) | 15. Finalize goals (a), objectives (b), key action steps (c), KPIs (d) and metrics(e).
May 7 (Planning Committee) | 16. Prepare, review and vet first draft of Educational Master Plan.
August, 2020 (College Opening Day) | 17. Vet and approval of final draft Educational Master Plan for publication
October | 18. Governance approval
November | 19. BOT approval